## Project Timeline
Project Timeline
Line chart that plots each milestone on the corresponding timeframe is in this cell.
Project Milestones
Date | Milestone | Assigned To | Position | Baseline | Column1
2020-02-10 | Project Start |  | 1 | 0
2020-03-31 | Ensure Compatability and Functionality of Buoy and Phone App |  | 5 | 0
2020-05-15 | Deliver Prototype to Teachers (MVP / Beta) |  | 2 | 0
2020-06-01 | Finalize User Guide |  | 3 | 0
2020-11-01 | Integrate Sensor Into Buoy |  | 5 | 0
2020-11-24 | Buoy 1.0 |  | 3 | 0
2020-12-01 | Android App 1.0 |  | 1 | 0
2021-01-10 | Web App Deployment Pipeline |  | 4 | 0
2021-03-10 | Web App 1.0 |  | 1 | 0
2021-04-30 | Official Website Release |  | 5 | 0
2021-05-10 | Android App 1.1 |  | 2 | 0
2021-05-25 | Buoy 1.1 |  | 3 | 0
2021-09-30 | Formal User Feedback - Storyboarding - Design Revisit |  | 4 | 0
2021-12-07 | Web 1.1 / Android 1.2 / Buoy 1.2 |  | 1 | 0
2022-03-01 | Web 1.2 / Android 1.3 / Buoy 1.3 |  | 4 | 0
2022-05-25 | Web 1.3 / Android 1.4 / Buoy 1.4 |  | 2 | 0
2022-06-01 | Project End & Party |  | 1 | 0
0
0
0
0
0
0
0